# Status Report

|  |  |  |  |
| --- | --- | --- | --- |
| SuperPoints, Team #9 | | | |
| **Date:** | 05/11/2019 | **Report for Week:** | 3 |
| **Client:** | Reese Williams | | |
| **Supervisor**: | Chi En Huang | | |

## Tasks Completed This Period

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Owner** | **Task Description** | **Estimated Hours** | **Actual Hours** | **Status** |
| Henry | Backend for app Admin, queries for KPI + html (26 hrs), aws/database documentation (4 hrs), bug fixes (4 hours) | 35 | 34 | Completed, DB guide needs to be revised |
| Harman | Setup auto emailer for admin kpi, setup schedule on server for admin to automatically receive emails monthly (24 hrs), bug fixes (4 hrs), | 35 | 28 | Completed |
| Oliver | Added saved state status to the app (5 hrs), started testing (3 hrs), bug fixes (7hrs), bluetooth beacon documentation (3hrs), changed DB object (9 hrs) , new settings table (5 hrs) | 35 | 32 | Completed, beacon guide needs to be revised |
| John | Completed analytics (3 hrs), bug fixing (4 hours), app admin (listview + details) (25 hours) | 35 | 32 | Completed |
| Everyone | Project Documentation | 4 | 3.5 | Completed |

## Tasks Planned but Not Completed

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Owner** | **Task Description** | **Estimated Hours** | **Actual Hours** | **Status** |
| Harman | user guide for the app (6 hrs) | 9 (in total) | 6 | In progress |
| Oliver | Started testing | 20 (in total) | 2 | In progress |
| John | Started testing | 20 (in total) | 2 | In progress |

## Tasks for Next Period

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Owner** | **Task Description** | **Estimated Hours** | **Planned Completion Date** | **Status** |
| Henry | Finish documentation, Testing + bug fixes, QR codes | 36 | May 17 | In progress |
| Harman | Finish documentation, Testing + bug fixes, QR codes | 36 | May 17 | In progress |
| John | Minor UI unification, Testing + bug fixes, QR codes | 36 | May 17 | In progress |
| Oliver | Finish documentation, Testing + bug fixes, QR codes | 36 | May 17 | In progress |
|  |  |  |  |  |

## Things the Team Supervisor Needs to Know

|  |  |  |
| --- | --- | --- |
| **Item Description** | **Potential Impact** | **Next Steps** |
|  |  |  |
|  |  |  |