## Instructions
Notes: | This is a template only. You may edit anything to better suit your project.
For unit of measure, use Hours, and don't get more granular than 0.5 hours (e.g. If something took 1 hour 15 minutes, round up to 1.5 hours)
You will not be evaluated on how close your estimates are. This document is for your interest, for comparison between estimates and actuals, and to help you improve your estimating skills.
Step 1 | During Stage 1
ROM | On the Summary sheet, enter Rough Order of Magnitude (ROM) high-level estimates in the pinkish squares, at the beginning of the project. This is meant to be total people-hours for the entire course.
Example: you estimate that 4 team members will spend 5 hours/week on dev, for 8 weeks. The ROM = 4 * 5 * 8 = 160 hours
Step 2 | At the start of Stage 2
Basic Estimates | On the Summary sheet, once you get into Stage 2 and tasks are broken down further, enter numbers in the Estimates column for each smaller task.
Step 3 | From Stage 2 onward
Actuals | As each week passes, each team member should update how much time they actually spent on each task (the Actuals).
This can be done either in the Summary Sheet, or in the Weekly sheet.
If Actuals are entered in the Weekly sheet, don't forget to total them properly in the Summary sheet. The Project Management area has been provided as an example.

## Summary
|  | ROM | Estimate | Actual | Variance (hours) | Variance (%)
Project Management |  | 270 | 0 | 70 | -70 | 0
| Meetings | 108 |  | 18 | -18 | 0
| Other communication | 18 |  | 1 | -1 | 0
| Documentation | 144 |  | 51 | -51 | 0
Development |  | 230 | 0 | 19 | -19 | 0
| Features | 80
| DB/Loc/Bluetooth refinement | 36 |  | 27
| User differentiation | 8
| GUI Draft | 6 |  | 2
| GUI Completion | 12 |  | 24
| Bluetooth reception test | 6
| Rough Bluetooth/Location Services & DB Creation | 24 |  | 10
| DB Design & Refinement of Bluetooth/Location Services Implementation | 32 |  | 9
| DB Table Creation | 16 |  | 2
| Research Bluetooth/Location/DB | 12 |  | 28
| Android/DB logic |  |  | 32
| Transmit Bluetooth information and retrieve successfully | 8
Testing | (This includes fixing bugs) | 182 | 0 | 2 | -2 | 0
| GUI Draft Test | 2
| GUI Completion Testing | 4
| Field Tests | 24
| DB/Loc/Blue testing | 12 |  | 2
| Hotfix pre-deployment testing | 48
| Final testing deployment testing | 92
Integration & Deployment |  | 124 | 0 | 0 | 0 | #DIV/0!
| Linkage between Bluetooth/Location Services | 16
| Establish SQL connection from Blue/Loc to DB | 8
| Deployment(refining everything) | 100

## Weekly
For certain tasks, track of time weekly, and summarize the total time on the first tab.
Do this for PM tasks, and optionally for any other tasks that span multiple weeks.
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | PHASE2: W1 | W2 | W3 | W4 | W5
Project Management
| Meetings | 2 | 2 | 2 | 3 | 3 | 2 |  | 2 | 2
| Other communication | W2: 0.5; W3: 0.5 | 12
| Documentation | W3: 8; W4: 6; W5: 4; W6: 3; W8: 3; W9: 3
Development | [13 empty] | 12
| Research | W3: 12; W4: 2
| Loc Implementation/refinement | W4: 6; W8: 1; W9: 3
| DB Design | W5: 3
| DB/AWS | W5: 4; W11: 4
| Bluetooth connection | W6: 3; W8: 3; W9: 3
| UI | W8: 2; W9: 8; W11: 8; W12: 8
| PHP script DB | W8: 5; W9: 2; W11: 4; W12: 8
| DB Logic/Android Logic | W11: 8; W12: 16
| DB Translator Logic | W11: 8